## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-1 | 2019-07-01 | 2019-07-15
Sprint-2 | 2019-07-16 | 2019-07-31

## 11_ClientProjectInfo
ProgramName | ProjectName | ClientName | HasWBS | ProjectType | DepartmentName | DivisionName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject
Angular Training | Angular Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | Angular Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
HTML / Bootstrapt / CSS / Javascript Training | HTML / Bootstrapt / CSS / Javascript Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | HTML / Bootstrapt / CSS / Javascript Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
React Training | React Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | React Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
.Net / .Net Core Training | .Net / .Net Core Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | .Net / .Net Core Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
.Net / .Net Core MVC Training | .Net / .Net Core MVC Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | .Net / .Net Core MVC Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
.Net / .Net Core Webforms Training | .Net / .Net Core Webforms Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | .Net / .Net Core Webforms Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
Blazor Training | Blazor Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | Blazor Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
MS SQL Training | MS SQL Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | MS SQL Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
MySQL Training | MySQL Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | MySQL Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
Postgress Training | Postgress Training | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | Postgress Training | ritesh.mangi@soartechnologies.net | TRUE | FALSE
Onboarding and Joining Formalities | Onboarding and Joining Formalities | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Onboarding and Joining Formalities | neha.r.mangi@soartechnologies.net | TRUE | TRUE
Legal Documentation | Legal Documentation | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Legal Documentation | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Orientation | Orientation | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Orientation | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Policy Updation | Policy Updation | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Policy Updation | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Offboarding | Offboarding | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Offboarding | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Managing Appriasals | Managing Appriasals | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Managing Appriasals | neha.r.mangi@soartechnologies.net | TRUE | FALSE
CV Screening | CV Screening | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | CV Screening | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Internview Scheduling | Internview Scheduling | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Internview Scheduling | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Offer Negotiation | Offer Negotiation | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Offer Negotiation | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Profile Review And Approval | Profile Review And Approval | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | Profile Review And Approval | neha.r.mangi@soartechnologies.net | TRUE | FALSE
KYC Updation | KYC Updation | SOAR Technologies - Internal Projects | FALSE | Service | HR | Management | KYC Updation | neha.r.mangi@soartechnologies.net | TRUE | FALSE
Assets And Inventory | Assets And Inventory | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | Assets And Inventory | ritesh.mangi@soartechnologies.net | TRUE | FALSE
Business Management | Business Management | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | Business Management | ritesh.mangi@soartechnologies.net | TRUE | FALSE
HR And Payroll | HR And Payroll | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | HR And Payroll | ritesh.mangi@soartechnologies.net | TRUE | FALSE
Office Management | Office Management | SOAR Technologies - Internal Projects | FALSE | Product | Full Stack Development | Project Management | Office Management | ritesh.mangi@soartechnologies.net | TRUE | FALSE

## 13_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Angular Training | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-20 | HTML / Bootstrapt / CSS / Javascript Training | 2025-08-20 | 2025-08-20 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-21 | React Training | 2025-08-21 | 2025-08-21 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-22 | .Net / .Net Core Training | 2025-08-22 | 2025-08-22 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-23 | .Net / .Net Core MVC Training | 2025-08-23 | 2025-08-23 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-24 | .Net / .Net Core Webforms Training | 2025-08-24 | 2025-08-24 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-25 | Blazor Training | 2025-08-25 | 2025-08-25 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-26 | MS SQL Training | 2025-08-26 | 2025-08-26 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-27 | MySQL Training | 2025-08-27 | 2025-08-27 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-28 | Postgress Training | 2025-08-28 | 2025-08-28 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-29 | Onboarding and Joining Formalities | 2025-08-29 | 2025-08-29 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-30 | Legal Documentation | 2025-08-30 | 2025-08-30 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-08-31 | Orientation | 2025-08-31 | 2025-08-31 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-01 | Policy Updation | 2025-09-01 | 2025-09-01 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-02 | Offboarding | 2025-09-02 | 2025-09-02 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-03 | Managing Appriasals | 2025-09-03 | 2025-09-03 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-04 | CV Screening | 2025-09-04 | 2025-09-04 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-05 | Internview Scheduling | 2025-09-05 | 2025-09-05 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-06 | Offer Negotiation | 2025-09-06 | 2025-09-06 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-07 | Profile Review And Approval | 2025-09-07 | 2025-09-07 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-08 | KYC Updation | 2025-09-08 | 2025-09-08 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-09 | Assets And Inventory | 2025-09-09 | 2025-09-09 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-10 | Business Management | 2025-09-10 | 2025-09-10 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-11 | HR And Payroll | 2025-09-11 | 2025-09-11 |  | TRUE | TRUE | FALSE
Development Started | Fist leve Done | 2025-09-12 | Office Management | 2025-09-12 | 2025-09-12 |  | TRUE | TRUE | FALSE

## 16_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Angular Training | Angular Training | AT | Development Started
HTML / Bootstrapt / CSS / Javascript Training | HTML / Bootstrapt / CSS / Javascript Training | Trainee | Development Started
React Training | React Training | Trainee | Development Started
.Net / .Net Core Training | .Net / .Net Core Training | Trainee | Development Started
.Net / .Net Core MVC Training | .Net / .Net Core MVC Training | Trainee | Development Started
.Net / .Net Core Webforms Training | .Net / .Net Core Webforms Training | Trainee | Development Started
Blazor Training | Blazor Training | Trainee | Development Started
MS SQL Training | MS SQL Training | Trainee | Development Started
MySQL Training | MySQL Training | Trainee | Development Started
Postgress Training | Postgress Training | Trainee | Development Started
Onboarding and Joining Formalities | Onboarding and Joining Formalities | Trainee | Development Started
Legal Documentation | Legal Documentation | Trainee | Development Started
Orientation | Orientation | Trainee | Development Started
Policy Updation | Policy Updation | Trainee | Development Started
Offboarding | Offboarding | Trainee | Development Started
Managing Appriasals | Managing Appriasals | Trainee | Development Started
CV Screening | CV Screening | Trainee | Development Started
Internview Scheduling | Internview Scheduling | Trainee | Development Started
Offer Negotiation | Offer Negotiation | Trainee | Development Started
Profile Review And Approval | Profile Review And Approval | Trainee | Development Started
KYC Updation | KYC Updation | Trainee | Development Started
Assets And Inventory | Assets And Inventory | Trainee | Development Started
Business Management | Business Management | Trainee | Development Started
HR And Payroll | HR And Payroll | Trainee | Development Started
Office Management | Office Management | Trainee | Development Started

## 17_ModuleFeature
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Angular Training | Angular Training | MTR | 133 | Web
HTML / Bootstrapt / CSS / Javascript Training | HTML / Bootstrapt / CSS / Javascript Training | UHC | 134 | Web
React Training | React Training | UIC | 135 | Web
.Net / .Net Core Training | .Net / .Net Core Training | UIP | 136 | Web
.Net / .Net Core MVC Training | .Net / .Net Core MVC Training | UTE | 137 | Web
.Net / .Net Core Webforms Training | .Net / .Net Core Webforms Training | UTS | 138 | Web
Blazor Training | Blazor Training | WTC | 139 | Web
MS SQL Training | MS SQL Training | TRE | 140 | Web
MySQL Training | MySQL Training | CNT | 141 | Web
Postgress Training | Postgress Training | DEF | 142 | Web
Onboarding and Joining Formalities | Onboarding and Joining Formalities | OJF | 143 | Web
Legal Documentation | Legal Documentation | LDN | 144 | Web
Orientation | Orientation | ORN | 145 | Web
Policy Updation | Policy Updation | PUN | 146 | Web
Offboarding | Offboarding | OFB | 147 | Web
Managing Appriasals | Managing Appriasals | MAA | 148 | Web
CV Screening | CV Screening | CVS | 149 | Web
Internview Scheduling | Internview Scheduling | INS | 150 | Web
Offer Negotiation | Offer Negotiation | OFN | 151 | Web
Profile Review And Approval | Profile Review And Approval | PRA | 152 | Web
KYC Updation | KYC Updation | KUN | 153 | Web
Assets And Inventory | Assets And Inventory | ASM | 154 | Web
Business Management | Business Management | BMO | 155 | Web
HR And Payroll | HR And Payroll | HAP | 156 | Web
Office Management | Office Management | OFG | 157 | Web

## 18_FeatureTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate | IsCompleted | IsCancelled | IsOnHold | IsBlocked | TaskCancellationReasonName | CancellationRemark
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Add Constraint | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Add New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Add Validation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Change Validation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Create CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Modify CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Remove Constraint | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Remove New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-1 | Sprint-1 | .Net / .Net Core MVC Training | Developer | Update Data strcture sheet | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Add Constraint | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Add New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Add Validation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Change Validation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Create CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Modify CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Remove Constraint | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Remove New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-1 | Sprint-1 | .Net / .Net Core Training | Developer | Update Data strcture sheet | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-1 | Sprint-1 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-2 | Sprint-2 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-2 | Sprint-2 | Onboarding and Joining Formalities | Human Resource Manager | Onboarding and Joining Formalities | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-2 | Sprint-2 | Legal Documentation | Human Resource Manager | Legal Documentation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-2 | Sprint-2 | Orientation | Human Resource Manager | Orientation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-2 | Sprint-2 | Policy Updation | Human Resource Manager | Policy Updation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-2 | Sprint-2 | Offboarding | Human Resource Manager | Offboarding | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-2 | Sprint-2 | Managing Appriasals | Human Resource Manager | Managing Appriasals | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-2 | Sprint-2 | CV Screening | Human Resource Manager | CV Screening | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-2 | Sprint-2 | Internview Scheduling | Human Resource Manager | Internview Scheduling | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-2 | Sprint-2 | Offer Negotiation | Human Resource Manager | Offer Negotiation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-2 | Sprint-2 | Profile Review And Approval | Human Resource Manager | Profile Review And Approval | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-2 | Sprint-2 | KYC Updation | Human Resource Manager | KYC Updation | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-2 | Sprint-2 | Assets And Inventory | Human Resource Manager | Modify CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-2 | Sprint-2 | Business Management | Human Resource Manager | Remove New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-2 | Sprint-2 | HR And Payroll | Human Resource Manager | Remove New Field | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Client not Responding | TaskRecurring-Hourly | Cancelled | Cancelled | Medium | 2 | Sprint-2 | Sprint-2 | Office Management | Developer | Modify CRUD | 0.25 | 2019-08-01 | 2024-08-01 | 8 | 2019-08-01 | 2024-08-01 | FALSE | TRUE | FALSE | FALSE | Incorrect or unclear requirements | Incorrect or unclear requirements

## 19_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-1 | Add Constraint
Sprint-2 | Add New Field
Sprint-2 | Add Validation
Sprint-1 | Change Validation
Sprint-2 | Create CRUD
Sprint-2 | Modify CRUD
Sprint-1 | Remove Constraint
Sprint-2 | Remove New Field
Sprint-2 | Update Data strcture sheet
Sprint-2 | Change Validation
Sprint-1 | Add New Field
Sprint-1 | Update Data strcture sheet
Sprint-2 | Onboarding and Joining Formalities
Sprint-1 | Legal Documentation
Sprint-2 | Orientation
Sprint-2 | Policy Updation
Sprint-1 | Offboarding
Sprint-2 | Managing Appriasals
Sprint-2 | CV Screening
Sprint-1 | Internview Scheduling
Sprint-2 | Offer Negotiation
Sprint-2 | Profile Review And Approval
Sprint-1 | KYC Updation

## 20_TaskAssignment
UniqueUserId | FeatureTaskName | TaskStatusName | StoryPoint | StartDate | EndDate | IsCompleted | IsOnHold
FFM000003 | Add Constraint | Assigned | 2 | 2019-08-01 | 2024-08-01 | TRUE | FALSE

## 21_WorkmanTimesheet
FillUpOn | UniqueUserId | StartTime | EndTime | TotalInTime | TaskName | ApprovedByName
2025-Sep-26 10:00:00 | FFM000003 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi