## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-3 | 2019-08-01 | 2019-08-15
Sprint-4 | 2019-08-16 | 2019-08-31

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | DivisionName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject
Sahakari Mandali - Windows based | Sahakari Mandali - Windows based | FALSE | Product | Full Stack Development | Project Management | Sahakari Mandali - Windows based | ritesh.mangi@soartechnologies.net | TRUE | FALSE

## 12_ProjectVersion
VersionText | ProjectName | EnvironmentTypeName | PlatformTypeName | VersionStartDate | VersionEndDate
1.0.0 | Sahakari Mandali - Windows based | Dev | Web | 2019-08-02

## 13_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-09-20 | Sahakari Mandali - Windows based | 2025-09-20 | 2025-09-20 |  | TRUE | TRUE | FALSE

## 14_LessonLearnPage
ProjectName | LearningAreaType | LearningDescription | Remarks
Sahakari Mandali - Windows based | Software Devlopment | Software Devlopment | Learned new techniques and queries

## 15_PlannedMeeting
UniqueUserId | ProjectName | MeetingPurpose | MeetingStartDateTime | MeetingEndDateTime
FFM000002 | Sahakari Mandali - Windows based | Standup Call | 2025-Sep-27 09:30:00 | 2025-Sep-27 10:30:00

## 16_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Sahakari Mandali - Windows based | Sahakari Mandali - Windows based | SM | Development Started

## 17_ModuleFeature
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Sahakari Mandali - Windows based | Sahakari Mandali - Windows based | SM | 134 | Web

## 18_FeatureTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate | IsCompleted | IsCancelled | IsOnHold | IsBlocked | TaskCancellationReasonName | CancellationRemark
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-3 | Sprint-3 | Sahakari Mandali - Windows based | Developer | Add Constraint | 0.25 | 2019-08-05 | 2019-10-01 | 8 | 2019-08-05 | 2019-10-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-3 | Sprint-3 | Sahakari Mandali - Windows based | Developer | Add New Field | 0.25 | 2019-08-06 | 2019-10-02 | 8 | 2019-08-06 | 2019-10-02 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-3 | Sprint-3 | Sahakari Mandali - Windows based | Developer | Add Validation | 0.25 | 2019-08-07 | 2019-10-03 | 8 | 2019-08-07 | 2019-10-03 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-3 | Sprint-3 | Sahakari Mandali - Windows based | Developer | Change Validation | 0.25 | 2019-08-08 | 2019-10-04 | 8 | 2019-08-08 | 2019-10-04 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-3 | Sprint-3 | Sahakari Mandali - Windows based | Developer | Create CRUD | 0.25 | 2019-08-09 | 2019-10-05 | 8 | 2019-08-09 | 2019-10-05 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-3 | Sprint-3 | Sahakari Mandali - Windows based | Developer | Modify CRUD | 0.25 | 2019-08-10 | 2019-10-06 | 8 | 2019-08-10 | 2019-10-06 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-4 | Sprint-4 | Sahakari Mandali - Windows based | Developer | Remove Constraint | 0.25 | 2019-08-11 | 2019-10-07 | 8 | 2019-08-11 | 2019-10-07 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-4 | Sprint-4 | Sahakari Mandali - Windows based | Developer | Remove New Field | 0.25 | 2019-08-12 | 2019-10-08 | 8 | 2019-08-12 | 2019-10-08 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-4 | Sprint-4 | Sahakari Mandali - Windows based | Developer | Update Data strcture sheet | 0.25 | 2019-08-13 | 2019-10-09 | 8 | 2019-08-13 | 2019-10-09 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Client not Responding | TaskRecurring-Hourly | Cancelled | Cancelled | Quick and Easy | 2 | Sprint-4 | Sprint-4 | Sahakari Mandali - Windows based | Developer | Update Data strcture sheet | 0.25 | 2019-08-13 | 2019-10-09 | 8 | 2019-08-13 | 2019-10-09 | FALSE | TRUE | FALSE | FALSE | Incorrect or unclear requirements | Incorrect or unclear requirements

## 20_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-3 | Add Constraint
Sprint-3 | Add New Field
Sprint-3 | Add Validation
Sprint-3 | Change Validation
Sprint-3 | Create CRUD
Sprint-4 | Modify CRUD
Sprint-4 | Remove Constraint
Sprint-4 | Remove New Field
Sprint-4 | Update Data strcture sheet

## 21_TaskAssignment
UniqueUserId | FeatureTaskName | TaskStatusName | StoryPoint | StartDate | EndDate
SOAR00001 | Change Validation | Initiated | 2 | 2019-08-05 | 2019-10-01

## 22_WorkmanTimesheet
FillUpOn | UniqueUserId | StartTime | EndTime | TotalInTime | TaskName | ApprovedByName
2025-Sep-27 10:25:00 | SOAR00001 | 2025-Sep-27 10:00:00 | 2025-Sep-27 12:30:00 | 2025-Sep-27 02:30:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-27 12:30:00 | SOAR00001 | 2025-Sep-27 12:30:00 | 2025-Sep-27 19:30:00 | 2025-Sep-27 08:00:00 | Change Validation | [FFM000002] - Neha Riteshkumar Mangi