## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-5 | 2019-09-01 | 2019-09-15
Sprint-6 | 2019-09-15 | 2019-09-30

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | DivisionName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject
BusinessDistributionSystem | BusinessDistributionSystem | TRUE | Product | Full Stack Development | MERN | BusinessDistributionSystem | ritesh.mangi@soartechnologies.net | FALSE | FALSE

## 12_ProjectVersion
VersionText | ProjectName | EnvironmentTypeName | PlatformTypeName | VersionStartDate | VersionEndDate
1.0.0 | Sahakari Mandali - Windows based | Dev | Web | 2019-08-02

## 13_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | BusinessDistributionSystem | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 14_LessonLearnPage
ProjectName | LearningAreaType | LearningDescription | Remarks
Sahakari Mandali - Windows based | Software Devlopment | Software Devlopment | Learned new techniques and queries

## 15_PlannedMeeting
UniqueUserId | ProjectName | MeetingPurpose | MeetingStartDateTime | MeetingEndDateTime
FFM000002 | Sahakari Mandali - Windows based | Standup Call | 2025-Sep-27 09:30:00 | 2025-Sep-27 10:30:00

## 16_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
BusinessDistributionSystem | Business Distribution System | BDS | Development Started

## 17_ModuleFeature
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Business Distribution System | MoneyTransfer | MTR | 133 | Web
Business Distribution System | System Role Customization | UHC | 134 | Web
Business Distribution System | BDS User Info Customization | UIC | 135 | Web
Business Distribution System | User Info Profile | UIP | 136 | Web
Business Distribution System | User Info Wise Trade Events | UTE | 137 | Web
Business Distribution System | User Info Wise Trade Settings | UTS | 138 | Web
Business Distribution System | Wallet Transaction | WTC | 139 | Web
Business Distribution System | Trade Execution | TRE | 140 | Web
Business Distribution System | Commission Type | CNT | 141 | Web
Business Distribution System | Default Settings | DEF | 142 | Web
Business Distribution System | Fortune Info | FOR | 143 | Web
Business Distribution System | Price Change | PRC | 144 | Web
Business Distribution System | Trade Classification | TCN | 145 | Web
Business Distribution System | Trade Event | TRE | 146 | Web
Business Distribution System | Trade Name | TRN | 147 | Web
Business Distribution System | Trade Rules | TRU | 148 | Web
Business Distribution System | Wallet Type | WLT | 149 | Web
Business Distribution System | Currency Type | CT | 150 | Web
Business Distribution System | Trade Commission | TC | 151 | Web

## 18_FeatureTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate | IsCompleted | IsCancelled | IsOnHold | IsBlocked | TaskCancellationReasonName | CancellationRemark
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Create CRUD | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Modify CRUD | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Add New Field | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Remove New Field | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Add Constraint | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Remove Constraint | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Add Validation | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Change Validation | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-5 | Sprint-5 | .Net / .Net Core MVC Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Create CRUD | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Modify CRUD | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Add New Field | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Remove New Field | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Add Constraint | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Remove Constraint | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Add Validation | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Change Validation | 0.25 | 2019-09-01 | 2019-09-10 | 8 | 2019-09-01 | 2019-09-10 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-5 | Sprint-5 | .Net / .Net Core Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-5 | Sprint-5 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-5 | Sprint-5 | Onboarding and Joining Formalities | Human Resource Manager | Create CRUD | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-5 | Sprint-5 | Legal Documentation | Human Resource Manager | Modify CRUD | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-5 | Sprint-5 | Orientation | Human Resource Manager | Add New Field | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-5 | Sprint-5 | Policy Updation | Human Resource Manager | Remove New Field | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-5 | Sprint-5 | Offboarding | Human Resource Manager | Add Constraint | 0.25 | 2019-09-10 | 2019-09-20 | 8 | 2019-09-10 | 2019-09-20 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-6 | Sprint-6 | Managing Appriasals | Human Resource Manager | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-6 | Sprint-6 | CV Screening | Human Resource Manager | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-6 | Sprint-6 | Internview Scheduling | Human Resource Manager | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-6 | Sprint-6 | Offer Negotiation | Human Resource Manager | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-6 | Sprint-6 | Profile Review And Approval | Human Resource Manager | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | KYC Updation | Human Resource Manager | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core MVC Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Create CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Modify CRUD | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove New Field | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Remove Constraint | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Add Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Change Validation | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Client not Responding | TaskRecurring-Hourly | Cancelled | Cancelled | Medium | 2 | Sprint-6 | Sprint-6 | .Net / .Net Core Webforms Training | Developer | Update Data strcture sheet | 0.25 | 2019-09-20 | 2019-09-30 | 8 | 2019-09-20 | 2019-09-30 | FALSE | TRUE | FALSE | FALSE | Incorrect or unclear requirements | Incorrect or unclear requirements

## 20_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-5 | Add Constraint
Sprint-5 | Add New Field
Sprint-5 | Add Validation
Sprint-5 | Change Validation
Sprint-5 | Create CRUD
Sprint-6 | Modify CRUD
Sprint-6 | Remove Constraint
Sprint-6 | Remove New Field
Sprint-6 | Update Data strcture sheet

## 21_TaskAssignment
UniqueUserId | FeatureTaskName | TaskStatusName | StoryPoint | StartDate | EndDate
SOAR00001 | Create CRUD | Transferred | 2 | 2019-09-01 | 2019-09-10

## 22_WorkmanTimesheet
FillUpOn | UniqueUserId | StartTime | EndTime | TotalInTime | TaskName | ApprovedByName
2025-Sep-28 09:25:00 | SOAR00001 | 2025-Sep-28 10:00:00 | 2025-Sep-28 10:25:00 | 2025-Sep-28 00:25:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 10:25:00 | SOAR00001 | 2025-Sep-28 10:25:00 | 2025-Sep-28 11:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 11:25:00 | SOAR00001 | 2025-Sep-28 11:25:00 | 2025-Sep-28 12:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 12:25:00 | SOAR00001 | 2025-Sep-28 12:25:00 | 2025-Sep-28 13:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 13:25:00 | SOAR00001 | 2025-Sep-28 13:25:00 | 2025-Sep-28 14:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 14:25:00 | SOAR00001 | 2025-Sep-28 14:25:00 | 2025-Sep-28 15:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 15:25:00 | SOAR00001 | 2025-Sep-28 15:25:00 | 2025-Sep-28 16:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 16:25:00 | SOAR00001 | 2025-Sep-28 16:25:00 | 2025-Sep-28 17:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 17:25:00 | SOAR00001 | 2025-Sep-28 17:25:00 | 2025-Sep-28 18:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-28 18:25:00 | SOAR00001 | 2025-Sep-28 18:25:00 | 2025-Sep-28 19:25:00 | 2025-Sep-28 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi