## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-9 | 2020-03-01 | 2020-03-15
Sprint-10 | 2020-03-16 | 2020-03-31

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | DivisionName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject
Invoicing | Invoicing | FALSE | Product | Full Stack Development | Web Design | Invoicing | nishit14@nhancedigital.com | FALSE | FALSE

## 12_ProjectVersion
VersionText | ProjectName | EnvironmentTypeName | PlatformTypeName | VersionStartDate | VersionEndDate
1.0.0 | Invoicing | Dev | Web | 2020-03-01

## 13_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Invoicing | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 14_LessonLearnPage
ProjectName | LearningAreaType | LearningDescription | Remarks
Invoicing | Software Devlopment | Software Devlopment | Learned new techniques and queries meeting and call

## 15_PlannedMeeting
UniqueUserId | ProjectName | MeetingPurpose | MeetingStartDateTime | MeetingEndDateTime
FFM000002 | Invoicing | Standup Call | 2025-Sep-30 09:50:00 | 2025-Sep-30 10:50:00

## 16_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Invoicing | Financial Accounting System | FAS | Development Started

## 17_ModuleFeature
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Financial Accounting System | Accounting Core Group | ACG | 30 | Web
Financial Accounting System | Accounting Group | AGP | 31 | Web
Financial Accounting System | Accounting Contra To Bank | ATB | 32 | Web
Financial Accounting System | Accounting Contra To Cash | ACC | 33 | Web
Financial Accounting System | Accounting JV | AJV | 34 | Web
Financial Accounting System | Accounting Ledger | ALR | 35 | Web
Financial Accounting System | Accounting Voucher | AVR | 36 | Web
Financial Accounting System | Account Cheque Book | ACB | 37 | Web
Financial Accounting System | Expenses | EPS | 38 | Web
Financial Accounting System | Financial Year Info | FYI | 39 | Web
Financial Accounting System | Taxation Info | TXI | 40 | Web
Financial Accounting System | Professional Tax Slabs | PTS | 41 | Web
Financial Accounting System | Salary Bracket | SLB | 42 | Web
Financial Accounting System | Salary Component | SLC | 43 | Web
Financial Accounting System | Salary Structure Definition | SSD | 44 | Web
Financial Accounting System | Salary Structure | SLT | 45 | Web
Financial Accounting System | Tax Type Info | TTI | 46 | Web
Financial Accounting System | Client Invoice Summary | CIS | 47 | Web
Financial Accounting System | Invoice Receipt | IR | 48 | Web
Financial Accounting System | Invoice Wise Tax Collection | IWTC | 49 | Web
Financial Accounting System | Invoice Data | ID | 50 | Web
Financial Accounting System | Invoice Wise Services | IWS | 51 | Web

## 18_FeatureTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate | IsCompleted | IsCancelled | IsOnHold | IsBlocked | TaskCancellationReasonName | CancellationRemark
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-9 | Sprint-10 | Client Invoice Summary | Developer | Create CRUD | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Modify CRUD | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Add New Field | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Remove New Field | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Add Constraint | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Remove Constraint | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Add Validation | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Change Validation | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-9 | Sprint-9 | Client Invoice Summary | Developer | Update Data strcture sheet | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Create CRUD | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Modify CRUD | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Add New Field | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Remove New Field | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Add Constraint | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Remove Constraint | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Add Validation | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Change Validation | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-9 | Sprint-9 | Invoice Receipt | Developer | Update Data strcture sheet | 0.25 | 2020-03-01 | 2020-04-01 | 8 | 2020-03-01 | 2020-04-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Wise Tax Collection | Developer | Create CRUD | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Wise Tax Collection | Developer | Modify CRUD | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Wise Tax Collection | Developer | Add New Field | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-9 | Sprint-9 | Invoice Wise Tax Collection | Developer | Remove New Field | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-9 | Sprint-9 | Invoice Wise Tax Collection | Developer | Add Constraint | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-9 | Sprint-9 | Invoice Wise Tax Collection | Developer | Remove Constraint | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-10 | Sprint-10 | Invoice Wise Tax Collection | Developer | Add Validation | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-10 | Sprint-10 | Invoice Wise Tax Collection | Developer | Change Validation | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-10 | Sprint-10 | Invoice Wise Tax Collection | Developer | Update Data strcture sheet | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Create CRUD | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Modify CRUD | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Add New Field | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Remove New Field | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Add Constraint | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Remove Constraint | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Add Validation | 0.25 | 2020-04-01 | 2020-06-01 | 8 | 2020-04-01 | 2020-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Change Validation | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-10 | Sprint-10 | Invoice Data | Developer | Update Data strcture sheet | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Create CRUD | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Modify CRUD | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Add New Field | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Remove New Field | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Add Constraint | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Remove Constraint | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Add Validation | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Change Validation | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | TRUE | FALSE | FALSE | FALSE | Not Cancelled | Not Cancelled
Client not Responding | TaskRecurring-Hourly | Cancelled | Cancelled | Medium | 2 | Sprint-10 | Sprint-10 | Invoice Wise Services | Developer | Update Data strcture sheet | 0.25 | 2020-06-01 | 2021-06-01 | 8 | 2020-06-01 | 2021-06-01 | FALSE | TRUE | FALSE | FALSE | Incorrect or unclear requirements | Incorrect or unclear requirements

## 19_TaskHurdle
FeatureTaskName | TaskHurdleTypeName | HurdleRemark | Resolution | HurdleStartDate | HurdleEndDate | ResolvedOn
Update Data strcture sheet | Hardware and Software Issue | Change software | Change software | 2020-03-01 | 2020-04-01 | 2020-04-01

## 20_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-10 | Add Constraint
Sprint-10 | Add New Field
Sprint-10 | Add Validation
Sprint-10 | Change Validation
Sprint-10 | Create CRUD
Sprint-10 | Modify CRUD
Sprint-10 | Remove Constraint
Sprint-10 | Remove New Field
Sprint-10 | Update Data strcture sheet

## 21_TaskAssignment
UniqueUserId | FeatureTaskName | TaskStatusName | StoryPoint | StartDate | EndDate
FFM000001 | Update Data strcture sheet | Completed | 2 | 2020-03-01 | 2020-04-01
FFM000001 | Add New Field | InProcess | 2 | 2020-03-01 | 2020-04-01
FFM000001 | Modify CRUD | Resolved | 2 | 2020-03-01 | 2020-04-01

## 22_WorkmanTimesheet
FillUpOn | UniqueUserId | StartTime | EndTime | TotalInTime | TaskName | ApprovedByName
2025-Sep-29 09:50:00 | TRN000001 | 2025-Sep-29 09:50:00 | 2025-Sep-29 10:50:00 | 2025-Sep-29 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-29 10:50:00 | TRN000001 | 2025-Sep-29 10:50:00 | 2025-Sep-29 11:50:00 | 2025-Sep-29 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-30 09:50:00 | TRN000001 | 2025-Sep-30 09:50:00 | 2025-Sep-30 10:50:00 | 2025-Sep-30 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-30 10:50:00 | TRN000001 | 2025-Sep-30 10:50:00 | 2025-Sep-30 11:50:00 | 2025-Sep-30 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-29 09:50:00 | TRN000002 | 2025-Sep-29 09:50:00 | 2025-Sep-29 10:50:00 | 2025-Sep-29 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-29 10:50:00 | TRN000002 | 2025-Sep-29 10:50:00 | 2025-Sep-29 11:50:00 | 2025-Sep-29 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-30 09:50:00 | TRN000002 | 2025-Sep-30 09:50:00 | 2025-Sep-30 10:50:00 | 2025-Sep-30 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-30 10:50:00 | TRN000002 | 2025-Sep-30 10:50:00 | 2025-Sep-30 11:50:00 | 2025-Sep-30 01:00:00 | Add Constraint | [FFM000002] - Neha Riteshkumar Mangi