## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-11 | 2020-06-01 | 2020-06-15
Sprint-12 | 2020-06-16 | 2020-06-30

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject
Rparking | Rparking | FALSE | Service | Full Stack Development | VS-Parking Project | nishit15@nhancedigital.com | FALSE | FALSE

## 12_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Rparking | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 13_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Rparking | VS3-Support and Maintenance | VS3 | Development Started

## 14_ModuleFeatures
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
VS3-Support and Maintenance | VS1-Support and Maintenance | VS1 | 469 | Web

## 15_ProjectTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-11 | Sprint-12 | VS1-Support and Maintenance | Developer | Coding and Testing | 0.25 | 2020-06-10 | 2020-07-25 | 8 | 2020-06-10 | 2020-07-25

## 17_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-11 | Add Constraint

## 18_TaskAssignment
UniqueUserId | FeatureTaskName | TaskStatusName | StoryPoint | StartDate | EndDate | IsCompleted | IsOnHold
FFM000001 | Add Constraint | Assigned | 5 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Add New Field | Hold | 6 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Add New Field | Initiated | 7 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Add Constraint | Cancelled | 8 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Add New Field | Completed | 9 | 2020-06-10 | 2020-07-25 | TRUE | TRUE
FFM000001 | Add Validation | InProcess | 10 | 2020-06-10 | 2020-07-25 | TRUE | TRUE
FFM000001 | Add Constraint | Resolved | 11 | 2020-06-10 | 2020-07-25 | TRUE | TRUE
FFM000001 | Change Validation | Transferred | 12 | 2020-06-10 | 2020-07-25 | TRUE | TRUE
FFM000001 | Create CRUD | Cancelled | 13 | 2020-06-10 | 2020-07-25 | TRUE | TRUE
FFM000001 | Add Constraint | Completed | 14 | 2020-06-10 | 2020-07-25 | TRUE | TRUE
FFM000001 | Modify CRUD | InProcess | 15 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Remove Constraint | Resolved | 16 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Remove New Field | Transferred | 17 | 2020-06-10 | 2020-07-25 | FALSE | FALSE
FFM000001 | Update Data strcture sheet | Transferred | 17 | 2020-06-10 | 2020-07-25 | FALSE | FALSE

## 19_WorkmanTimesheet
FillUpOn | UniqueUserId | StepInAt | StepOutAt | TotalInTime | TimesheetTime | BillableTime | OfficeAcitivityTime | IdleTime | TaskName | StatusName | IsWorkDone | AttachInAppriasal | ValuableContribution | UserPreferredName
2025-oct-01 09:30:00 | SOAR00002 | 2025-oct-01 09:30:00 | 2025-oct-01 10:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi