## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-41 | 2023-04-01 | 2023-04-15
Sprint-42 | 2023-04-15 | 2023-04-30

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject | AllocationFrequencyName | ProjectRoleName
Event Management System | Event Management System | TRUE | Product | Full Stack Development | Event Management System | ritesh.mangi@soartechnologies.net | FALSE | FALSE | Allocated-Hour | Project Management

## 12_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Event Management System | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 13_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Event Management System | Event Management System | EMS | Development Started

## 14_ModuleFeatures
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Event Management System | Event Audiance | DEF | 748 | Web
Event Management System | Event Cancellation Policy | CNT | 749 | Web
Event Management System | Event Categories | CNT | 745 | Web
Event Management System | Event Categories Association | DEF | 746 | Web
Event Management System | Event Feedback Parameters | CNT | 747 | Web
Event Management System | Event For Artist | DEF | 750 | Web
Event Management System | Event Info | CNT | 751 | Web
Event Management System | Event Overall Rating And Feedback | DEF | 752 | Web
Event Management System | Event Parameter Rating And Feedback | CNT | 753 | Web
Event Management System | Event Pricing | DEF | 754 | Web
Event Management System | Event Revenue Collection | CNT | 755 | Web
Event Management System | Event Revenue Tax Collection | DEF | 756 | Web
Event Management System | Event Ticket Transfer | CNT | 757 | Web
Event Management System | Feedback Parameter | DEF | 758 | Web
Event Management System | Organizer Info | CNT | 759 | Web
Event Management System | Organizer Partnership | DEF | 760 | Web
Event Management System | Sitting Classification | CNT | 761 | Web
Event Management System | Social Media Sharing | DEF | 762 | Web
Event Management System | Sub Venue Info | CNT | 763 | Web
Event Management System | Sub Venue Sitting Arrangement | DEF | 764 | Web
Event Management System | Sub Venue Sitting Classification | CNT | 765 | Web
Event Management System | Venue Info | DEF | 766 | Web
Event Management System | Venue Sitting Arrangement | CNT | 767 | Web
Event Management System | Venue Sitting Classification | DEF | 768 | Web

## 15_ProjectTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Add Constraint | 36 | 2023-04-01 | 2024-04-01 | 36 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Add New Field | 37 | 2023-04-01 | 2024-04-01 | 37 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Add Validation | 38 | 2023-04-01 | 2024-04-01 | 38 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Change Validation | 39 | 2023-04-01 | 2024-04-01 | 39 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Create CRUD | 40 | 2023-04-01 | 2024-04-01 | 40 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Modify CRUD | 41 | 2023-04-01 | 2024-04-01 | 41 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Remove Constraint | 42 | 2023-04-01 | 2024-04-01 | 42 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Remove New Field | 43 | 2023-04-01 | 2024-04-01 | 43 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-41 | Sprint-42 | Event Audiance | Developer | Update Data strcture sheet | 44 | 2023-04-01 | 2024-04-01 | 44 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Add Constraint | 45 | 2023-04-01 | 2024-04-01 | 45 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Add New Field | 46 | 2023-04-01 | 2024-04-01 | 46 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Add Validation | 47 | 2023-04-01 | 2024-04-01 | 47 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Change Validation | 48 | 2023-04-01 | 2024-04-01 | 48 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Create CRUD | 49 | 2023-04-01 | 2024-04-01 | 49 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Modify CRUD | 50 | 2023-04-01 | 2024-04-01 | 50 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Remove Constraint | 51 | 2023-04-01 | 2024-04-01 | 51 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Remove New Field | 52 | 2023-04-01 | 2024-04-01 | 52 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-41 | Sprint-42 | Event Cancellation Policy | Developer | Update Data strcture sheet | 53 | 2023-04-01 | 2024-04-01 | 53 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Add Constraint | 54 | 2023-04-01 | 2024-04-01 | 54 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Add New Field | 55 | 2023-04-01 | 2024-04-01 | 55 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Add Validation | 56 | 2023-04-01 | 2024-04-01 | 56 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Change Validation | 57 | 2023-04-01 | 2024-04-01 | 57 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-41 | Sprint-42 | Event Categories | Developer | Create CRUD | 58 | 2023-04-01 | 2024-04-01 | 58 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Modify CRUD | 59 | 2023-04-01 | 2024-04-01 | 59 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Remove Constraint | 60 | 2023-04-01 | 2024-04-01 | 60 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Remove New Field | 61 | 2023-04-01 | 2024-04-01 | 61 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-41 | Sprint-42 | Event Categories | Developer | Update Data strcture sheet | 62 | 2023-04-01 | 2024-04-01 | 62 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Add Constraint | 63 | 2023-04-01 | 2024-04-01 | 63 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Add New Field | 64 | 2023-04-01 | 2024-04-01 | 64 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Add Validation | 65 | 2023-04-01 | 2024-04-01 | 65 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Change Validation | 66 | 2023-04-01 | 2024-04-01 | 66 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Create CRUD | 67 | 2023-04-01 | 2024-04-01 | 67 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Modify CRUD | 68 | 2023-04-01 | 2024-04-01 | 68 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Remove Constraint | 69 | 2023-04-01 | 2024-04-01 | 69 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Remove New Field | 70 | 2023-04-01 | 2024-04-01 | 70 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Event Categories Association | Developer | Update Data strcture sheet | 71 | 2023-04-01 | 2024-04-01 | 71 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Add Constraint | 72 | 2023-04-01 | 2024-04-01 | 72 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Add New Field | 73 | 2023-04-01 | 2024-04-01 | 73 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 3 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Add Validation | 74 | 2023-04-01 | 2024-04-01 | 74 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 4 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Change Validation | 75 | 2023-04-01 | 2024-04-01 | 75 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 5 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Create CRUD | 76 | 2023-04-01 | 2024-04-01 | 76 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 6 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Modify CRUD | 77 | 2023-04-01 | 2024-04-01 | 77 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 7 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Remove Constraint | 78 | 2023-04-01 | 2024-04-01 | 78 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 8 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Remove New Field | 79 | 2023-04-01 | 2024-04-01 | 79 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 9 | Sprint-41 | Sprint-42 | Event Feedback Parameters | Developer | Update Data strcture sheet | 80 | 2023-04-01 | 2024-04-01 | 80 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 10 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Add Constraint | 81 | 2023-04-01 | 2024-04-01 | 81 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 11 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Add New Field | 82 | 2023-04-01 | 2024-04-01 | 82 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 12 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Add Validation | 83 | 2023-04-01 | 2024-04-01 | 83 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 13 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Change Validation | 84 | 2023-04-01 | 2024-04-01 | 84 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 14 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Create CRUD | 85 | 2023-04-01 | 2024-04-01 | 85 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 15 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Modify CRUD | 86 | 2023-04-01 | 2024-04-01 | 86 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 16 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Remove Constraint | 87 | 2023-04-01 | 2024-04-01 | 87 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 17 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Remove New Field | 88 | 2023-04-01 | 2024-04-01 | 88 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 18 | Sprint-41 | Sprint-42 | Event For Artist | Developer | Update Data strcture sheet | 89 | 2023-04-01 | 2024-04-01 | 89 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 19 | Sprint-41 | Sprint-42 | Event Info | Developer | Add Constraint | 90 | 2023-04-01 | 2024-04-01 | 90 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 20 | Sprint-41 | Sprint-42 | Event Info | Developer | Add New Field | 91 | 2023-04-01 | 2024-04-01 | 91 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 21 | Sprint-41 | Sprint-42 | Event Info | Developer | Add Validation | 92 | 2023-04-01 | 2024-04-01 | 92 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 22 | Sprint-41 | Sprint-42 | Event Info | Developer | Change Validation | 93 | 2023-04-01 | 2024-04-01 | 93 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 23 | Sprint-41 | Sprint-42 | Event Info | Developer | Create CRUD | 94 | 2023-04-01 | 2024-04-01 | 94 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 24 | Sprint-41 | Sprint-42 | Event Info | Developer | Modify CRUD | 95 | 2023-04-01 | 2024-04-01 | 95 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 25 | Sprint-41 | Sprint-42 | Event Info | Developer | Remove Constraint | 96 | 2023-04-01 | 2024-04-01 | 96 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 26 | Sprint-41 | Sprint-42 | Event Info | Developer | Remove New Field | 97 | 2023-04-01 | 2024-04-01 | 97 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 27 | Sprint-41 | Sprint-42 | Event Info | Developer | Update Data strcture sheet | 98 | 2023-04-01 | 2024-04-01 | 98 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 28 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Add Constraint | 99 | 2023-04-01 | 2024-04-01 | 99 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 29 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Add New Field | 36 | 2023-04-01 | 2024-04-01 | 36 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 30 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Add Validation | 37 | 2023-04-01 | 2024-04-01 | 37 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 31 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Change Validation | 38 | 2023-04-01 | 2024-04-01 | 38 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 32 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Create CRUD | 39 | 2023-04-01 | 2024-04-01 | 39 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 33 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Modify CRUD | 40 | 2023-04-01 | 2024-04-01 | 40 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 34 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Remove Constraint | 41 | 2023-04-01 | 2024-04-01 | 41 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 35 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Remove New Field | 42 | 2023-04-01 | 2024-04-01 | 42 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 36 | Sprint-41 | Sprint-42 | Event Overall Rating And Feedback | Developer | Update Data strcture sheet | 43 | 2023-04-01 | 2024-04-01 | 43 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 37 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Add Constraint | 44 | 2023-04-01 | 2024-04-01 | 44 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 38 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Add New Field | 45 | 2023-04-01 | 2024-04-01 | 45 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 39 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Add Validation | 46 | 2023-04-01 | 2024-04-01 | 46 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 40 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Change Validation | 47 | 2023-04-01 | 2024-04-01 | 47 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 41 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Create CRUD | 48 | 2023-04-01 | 2024-04-01 | 48 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 42 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Modify CRUD | 49 | 2023-04-01 | 2024-04-01 | 49 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 43 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Remove Constraint | 50 | 2023-04-01 | 2024-04-01 | 50 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 44 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Remove New Field | 51 | 2023-04-01 | 2024-04-01 | 51 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 45 | Sprint-41 | Sprint-42 | Event Parameter Rating And Feedback | Developer | Update Data strcture sheet | 52 | 2023-04-01 | 2024-04-01 | 52 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 46 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Add Constraint | 53 | 2023-04-01 | 2024-04-01 | 53 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 47 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Add New Field | 54 | 2023-04-01 | 2024-04-01 | 54 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 48 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Add Validation | 55 | 2023-04-01 | 2024-04-01 | 55 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 49 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Change Validation | 56 | 2023-04-01 | 2024-04-01 | 56 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 50 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Create CRUD | 57 | 2023-04-01 | 2024-04-01 | 57 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 51 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Modify CRUD | 58 | 2023-04-01 | 2024-04-01 | 58 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 52 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Remove Constraint | 59 | 2023-04-01 | 2024-04-01 | 59 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 53 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Remove New Field | 60 | 2023-04-01 | 2024-04-01 | 60 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 54 | Sprint-41 | Sprint-42 | Event Pricing | Developer | Update Data strcture sheet | 61 | 2023-04-01 | 2024-04-01 | 61 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 55 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Add Constraint | 62 | 2023-04-01 | 2024-04-01 | 62 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 56 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Add New Field | 63 | 2023-04-01 | 2024-04-01 | 63 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 57 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Add Validation | 64 | 2023-04-01 | 2024-04-01 | 64 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 58 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Change Validation | 65 | 2023-04-01 | 2024-04-01 | 65 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 59 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Create CRUD | 66 | 2023-04-01 | 2024-04-01 | 66 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 60 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Modify CRUD | 67 | 2023-04-01 | 2024-04-01 | 67 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 61 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Remove Constraint | 68 | 2023-04-01 | 2024-04-01 | 68 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 62 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Remove New Field | 69 | 2023-04-01 | 2024-04-01 | 69 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 63 | Sprint-41 | Sprint-42 | Event Revenue Collection | Developer | Update Data strcture sheet | 70 | 2023-04-01 | 2024-04-01 | 70 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 64 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Add Constraint | 71 | 2023-04-01 | 2024-04-01 | 71 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 65 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Add New Field | 72 | 2023-04-01 | 2024-04-01 | 72 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 66 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Add Validation | 73 | 2023-04-01 | 2024-04-01 | 73 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 67 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Change Validation | 74 | 2023-04-01 | 2024-04-01 | 74 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 68 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Create CRUD | 75 | 2023-04-01 | 2024-04-01 | 75 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 69 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Modify CRUD | 76 | 2023-04-01 | 2024-04-01 | 76 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 70 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Remove Constraint | 77 | 2023-04-01 | 2024-04-01 | 77 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 71 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Remove New Field | 78 | 2023-04-01 | 2024-04-01 | 78 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 72 | Sprint-41 | Sprint-42 | Event Revenue Tax Collection | Developer | Update Data strcture sheet | 79 | 2023-04-01 | 2024-04-01 | 79 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 73 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Add Constraint | 80 | 2023-04-01 | 2024-04-01 | 80 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 74 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Add New Field | 81 | 2023-04-01 | 2024-04-01 | 81 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 75 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Add Validation | 82 | 2023-04-01 | 2024-04-01 | 82 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 76 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Change Validation | 83 | 2023-04-01 | 2024-04-01 | 83 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 77 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Create CRUD | 84 | 2023-04-01 | 2024-04-01 | 84 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 78 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Modify CRUD | 85 | 2023-04-01 | 2024-04-01 | 85 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 79 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Remove Constraint | 86 | 2023-04-01 | 2024-04-01 | 86 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 80 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Remove New Field | 87 | 2023-04-01 | 2024-04-01 | 87 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 81 | Sprint-41 | Sprint-42 | Event Ticket Transfer | Developer | Update Data strcture sheet | 88 | 2023-04-01 | 2024-04-01 | 88 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 82 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Add Constraint | 89 | 2023-04-01 | 2024-04-01 | 89 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 83 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Add New Field | 90 | 2023-04-01 | 2024-04-01 | 90 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 84 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Add Validation | 91 | 2023-04-01 | 2024-04-01 | 91 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 85 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Change Validation | 92 | 2023-04-01 | 2024-04-01 | 92 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 86 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Create CRUD | 93 | 2023-04-01 | 2024-04-01 | 93 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 87 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Modify CRUD | 94 | 2023-04-01 | 2024-04-01 | 94 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 88 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Remove Constraint | 95 | 2023-04-01 | 2024-04-01 | 95 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 89 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Remove New Field | 96 | 2023-04-01 | 2024-04-01 | 96 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 90 | Sprint-41 | Sprint-42 | Feedback Parameter | Developer | Update Data strcture sheet | 97 | 2023-04-01 | 2024-04-01 | 97 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 91 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Add Constraint | 98 | 2023-04-01 | 2024-04-01 | 98 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 92 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Add New Field | 99 | 2023-04-01 | 2024-04-01 | 99 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 93 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Add Validation | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 94 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Change Validation | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 95 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Create CRUD | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 96 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Modify CRUD | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 97 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Remove Constraint | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 98 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Remove New Field | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 99 | Sprint-41 | Sprint-42 | Organizer Info | Developer | Update Data strcture sheet | 8 | 2023-04-01 | 2024-04-01 | 8 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Add Constraint | 9 | 2023-04-01 | 2024-04-01 | 9 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Add New Field | 10 | 2023-04-01 | 2024-04-01 | 10 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Add Validation | 11 | 2023-04-01 | 2024-04-01 | 11 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Change Validation | 12 | 2023-04-01 | 2024-04-01 | 12 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Create CRUD | 13 | 2023-04-01 | 2024-04-01 | 13 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Modify CRUD | 14 | 2023-04-01 | 2024-04-01 | 14 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Remove Constraint | 15 | 2023-04-01 | 2024-04-01 | 15 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Remove New Field | 16 | 2023-04-01 | 2024-04-01 | 16 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Organizer Partnership | Developer | Update Data strcture sheet | 17 | 2023-04-01 | 2024-04-01 | 17 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Add Constraint | 36 | 2023-04-01 | 2024-04-01 | 36 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Add New Field | 37 | 2023-04-01 | 2024-04-01 | 37 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Add Validation | 38 | 2023-04-01 | 2024-04-01 | 38 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Change Validation | 39 | 2023-04-01 | 2024-04-01 | 39 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Create CRUD | 40 | 2023-04-01 | 2024-04-01 | 40 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Modify CRUD | 41 | 2023-04-01 | 2024-04-01 | 41 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Remove Constraint | 42 | 2023-04-01 | 2024-04-01 | 42 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Remove New Field | 43 | 2023-04-01 | 2024-04-01 | 43 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sitting Classification | Developer | Update Data strcture sheet | 44 | 2023-04-01 | 2024-04-01 | 44 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Add Constraint | 45 | 2023-04-01 | 2024-04-01 | 45 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Add New Field | 46 | 2023-04-01 | 2024-04-01 | 46 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Add Validation | 47 | 2023-04-01 | 2024-04-01 | 47 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Change Validation | 48 | 2023-04-01 | 2024-04-01 | 48 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Create CRUD | 49 | 2023-04-01 | 2024-04-01 | 49 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Modify CRUD | 50 | 2023-04-01 | 2024-04-01 | 50 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Remove Constraint | 51 | 2023-04-01 | 2024-04-01 | 51 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Remove New Field | 52 | 2023-04-01 | 2024-04-01 | 52 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Social Media Sharing | Developer | Update Data strcture sheet | 53 | 2023-04-01 | 2024-04-01 | 53 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Add Constraint | 54 | 2023-04-01 | 2024-04-01 | 54 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Add New Field | 55 | 2023-04-01 | 2024-04-01 | 55 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Add Validation | 56 | 2023-04-01 | 2024-04-01 | 56 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Change Validation | 57 | 2023-04-01 | 2024-04-01 | 57 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Create CRUD | 58 | 2023-04-01 | 2024-04-01 | 58 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Modify CRUD | 59 | 2023-04-01 | 2024-04-01 | 59 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Remove Constraint | 60 | 2023-04-01 | 2024-04-01 | 60 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Remove New Field | 61 | 2023-04-01 | 2024-04-01 | 61 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sub Venue Info | Developer | Update Data strcture sheet | 62 | 2023-04-01 | 2024-04-01 | 62 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Add Constraint | 63 | 2023-04-01 | 2024-04-01 | 63 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Add New Field | 64 | 2023-04-01 | 2024-04-01 | 64 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 3 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Add Validation | 65 | 2023-04-01 | 2024-04-01 | 65 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 4 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Change Validation | 66 | 2023-04-01 | 2024-04-01 | 66 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 5 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Create CRUD | 67 | 2023-04-01 | 2024-04-01 | 67 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 6 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Modify CRUD | 68 | 2023-04-01 | 2024-04-01 | 68 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 7 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Remove Constraint | 69 | 2023-04-01 | 2024-04-01 | 69 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 8 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Remove New Field | 70 | 2023-04-01 | 2024-04-01 | 70 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 9 | Sprint-41 | Sprint-42 | Sub Venue Sitting Arrangement | Developer | Update Data strcture sheet | 71 | 2023-04-01 | 2024-04-01 | 71 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 10 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Add Constraint | 72 | 2023-04-01 | 2024-04-01 | 72 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 11 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Add New Field | 73 | 2023-04-01 | 2024-04-01 | 73 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 12 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Add Validation | 74 | 2023-04-01 | 2024-04-01 | 74 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 13 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Change Validation | 75 | 2023-04-01 | 2024-04-01 | 75 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 14 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Create CRUD | 76 | 2023-04-01 | 2024-04-01 | 76 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 15 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Modify CRUD | 77 | 2023-04-01 | 2024-04-01 | 77 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 16 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Remove Constraint | 78 | 2023-04-01 | 2024-04-01 | 78 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 17 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Remove New Field | 79 | 2023-04-01 | 2024-04-01 | 79 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 18 | Sprint-41 | Sprint-42 | Sub Venue Sitting Classification | Developer | Update Data strcture sheet | 80 | 2023-04-01 | 2024-04-01 | 80 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 19 | Sprint-41 | Sprint-42 | Venue Info | Developer | Add Constraint | 81 | 2023-04-01 | 2024-04-01 | 81 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 20 | Sprint-41 | Sprint-42 | Venue Info | Developer | Add New Field | 82 | 2023-04-01 | 2024-04-01 | 82 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 21 | Sprint-41 | Sprint-42 | Venue Info | Developer | Add Validation | 83 | 2023-04-01 | 2024-04-01 | 83 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 22 | Sprint-41 | Sprint-42 | Venue Info | Developer | Change Validation | 84 | 2023-04-01 | 2024-04-01 | 84 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 23 | Sprint-41 | Sprint-42 | Venue Info | Developer | Create CRUD | 85 | 2023-04-01 | 2024-04-01 | 85 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 24 | Sprint-41 | Sprint-42 | Venue Info | Developer | Modify CRUD | 86 | 2023-04-01 | 2024-04-01 | 86 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 25 | Sprint-41 | Sprint-42 | Venue Info | Developer | Remove Constraint | 87 | 2023-04-01 | 2024-04-01 | 87 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 26 | Sprint-41 | Sprint-42 | Venue Info | Developer | Remove New Field | 88 | 2023-04-01 | 2024-04-01 | 88 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 27 | Sprint-41 | Sprint-42 | Venue Info | Developer | Update Data strcture sheet | 89 | 2023-04-01 | 2024-04-01 | 89 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 28 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Add Constraint | 90 | 2023-04-01 | 2024-04-01 | 90 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 29 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Add New Field | 91 | 2023-04-01 | 2024-04-01 | 91 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 30 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Add Validation | 92 | 2023-04-01 | 2024-04-01 | 92 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 31 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Change Validation | 93 | 2023-04-01 | 2024-04-01 | 93 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 32 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Create CRUD | 94 | 2023-04-01 | 2024-04-01 | 94 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 33 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Modify CRUD | 95 | 2023-04-01 | 2024-04-01 | 95 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 34 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Remove Constraint | 96 | 2023-04-01 | 2024-04-01 | 96 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 35 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Remove New Field | 97 | 2023-04-01 | 2024-04-01 | 97 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 36 | Sprint-41 | Sprint-42 | Venue Sitting Arrangement | Developer | Update Data strcture sheet | 98 | 2023-04-01 | 2024-04-01 | 98 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 37 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Add Constraint | 99 | 2023-04-01 | 2024-04-01 | 99 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 38 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Add New Field | 36 | 2023-04-01 | 2024-04-01 | 36 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 39 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Add Validation | 37 | 2023-04-01 | 2024-04-01 | 37 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 40 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Change Validation | 38 | 2023-04-01 | 2024-04-01 | 38 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 41 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Create CRUD | 39 | 2023-04-01 | 2024-04-01 | 39 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 42 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Modify CRUD | 40 | 2023-04-01 | 2024-04-01 | 40 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 43 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Remove Constraint | 41 | 2023-04-01 | 2024-04-01 | 41 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 44 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Remove New Field | 42 | 2023-04-01 | 2024-04-01 | 42 | 2023-04-01 | 2024-04-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 45 | Sprint-41 | Sprint-42 | Venue Sitting Classification | Developer | Update Data strcture sheet | 43 | 2023-04-01 | 2024-04-01 | 43 | 2023-04-01 | 2024-04-01

## 17_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-41 | Add Constraint
Sprint-41 | Add New Field
Sprint-41 | Add Validation
Sprint-41 | Change Validation
Sprint-41 | Create CRUD
Sprint-41 | Modify CRUD
Sprint-41 | Remove Constraint
Sprint-41 | Remove New Field
Sprint-41 | Update Data strcture sheet

## 18_TaskAssignment
UniqueUserId | FeatureTaskName | TaskHurdleName | StoryPoint | StartDate | EndDate | IsCompleted | IsOnHold
FFM000001 | Add Constraint | Unfamilar with subject | 65 | 2023-04-01 | 2024-04-01 | TRUE | FALSE

## 19_WorkmanTimesheet
FillUpOn | UniqueUserId | StepInAt | StepOutAt | TotalInTime | TimesheetTime | BillableTime | OfficeAcitivityTime | IdleTime | TaskName | StatusName | IsWorkDone | AttachInAppriasal | ValuableContribution | UserPreferredName
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi