## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-47 | 2024-04-01 | 2024-04-15
Sprint-48 | 2024-04-16 | 31-04-2024

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject | AllocationFrequencyName | ProjectRoleName
Sarvadhan Savardhan | Sarvadhan Savardhan | TRUE | Product | Full Stack Development | Sarvadhan Savardhan | ritesh.mangi@soartechnologies.net | FALSE | FALSE | Allocated-Hour | Project Management

## 12_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Sarvadhan Savardhan | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 13_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Sarvadhan Savardhan | Portfolio View Review | PVR | Development Started
Sarvadhan Savardhan | Loan Management | LON | Development Started

## 14_ModuleFeatures
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Portfolio View Review | Brokerage Houses Info | DEF | 728 | Web
Portfolio View Review | Charges Type | CNT | 729 | Web
Portfolio View Review | Market Cap Info | DEF | 730 | Web
Portfolio View Review | Segment Info | CNT | 731 | Web
Portfolio View Review | Stock And Commodity Info | DEF | 732 | Web
Portfolio View Review | Stock Cap Classification | CNT | 733 | Web
Portfolio View Review | Stock Segment | DEF | 734 | Web
Portfolio View Review | Charges Info | CNT | 735 | Web
Portfolio View Review | Exposure Info | DEF | 736 | Web
Portfolio View Review | Stock Performance | CNT | 737 | Web
Portfolio View Review | Stock TechnicalInfo | DEF | 738 | Web
Portfolio View Review | Stock Transaction | CNT | 739 | Web
Portfolio View Review | User Broker | DEF | 740 | Web
Portfolio View Review | User Segment | CNT | 741 | Web
Portfolio View Review | User Stock | DEF | 742 | Web
Loan Management | Income Hair Cut | DEF | 800 | Web
Loan Management | Loan Cheque Mortgage | CNT | 801 | Web
Loan Management | Loan Cheque Transaction | DEF | 802 | Web
Loan Management | Loan Closure | CNT | 803 | Web
Loan Management | Loan Disburshment | DEF | 804 | Web
Loan Management | Loan Proposal | CNT | 805 | Web
Loan Management | Loan Request | DEF | 806 | Web
Loan Management | Loan To NPA | CNT | 807 | Web

## 15_ProjectTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Add Constraint | 1.25 | 2024-04-01 | 2024-09-01 | 9 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Add New Field | 2.25 | 2024-04-01 | 2024-09-01 | 10 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Add Validation | 3.25 | 2024-04-01 | 2024-09-01 | 11 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Change Validation | 4.25 | 2024-04-01 | 2024-09-01 | 12 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Create CRUD | 5.25 | 2024-04-01 | 2024-09-01 | 13 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Modify CRUD | 6.25 | 2024-04-01 | 2024-09-01 | 14 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Remove Constraint | 7.25 | 2024-04-01 | 2024-09-01 | 15 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Remove New Field | 8.25 | 2024-04-01 | 2024-09-01 | 16 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-47 | Sprint-47 | Brokerage Houses Info | Developer | Update Data strcture sheet | 9.25 | 2024-04-01 | 2024-09-01 | 17 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Add Constraint | 10.25 | 2024-04-01 | 2024-09-01 | 18 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Add New Field | 11.25 | 2024-04-01 | 2024-09-01 | 19 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Add Validation | 12.25 | 2024-04-01 | 2024-09-01 | 20 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Change Validation | 13.25 | 2024-04-01 | 2024-09-01 | 21 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Create CRUD | 14.25 | 2024-04-01 | 2024-09-01 | 22 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Modify CRUD | 15.25 | 2024-04-01 | 2024-09-01 | 23 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Remove Constraint | 16.25 | 2024-04-01 | 2024-09-01 | 24 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Charges Type | Developer | Remove New Field | 17.25 | 2024-04-01 | 2024-09-01 | 25 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-47 | Sprint-47 | Charges Type | Developer | Update Data strcture sheet | 18.25 | 2024-04-01 | 2024-09-01 | 26 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Add Constraint | 19.25 | 2024-04-01 | 2024-09-01 | 27 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Add New Field | 20.25 | 2024-04-01 | 2024-09-01 | 28 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Add Validation | 21.25 | 2024-04-01 | 2024-09-01 | 29 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Change Validation | 22.25 | 2024-04-01 | 2024-09-01 | 30 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Create CRUD | 23.25 | 2024-04-01 | 2024-09-01 | 31 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Modify CRUD | 24.25 | 2024-04-01 | 2024-09-01 | 32 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Remove Constraint | 25.25 | 2024-04-01 | 2024-09-01 | 33 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-47 | Sprint-47 | Market Cap Info | Developer | Remove New Field | 26.25 | 2024-04-01 | 2024-09-01 | 34 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-48 | Sprint-48 | Market Cap Info | Developer | Update Data strcture sheet | 27.25 | 2024-04-01 | 2024-09-01 | 35 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-48 | Sprint-48 | Segment Info | Developer | Add Constraint | 28.25 | 2024-04-01 | 2024-09-01 | 36 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-48 | Sprint-48 | Segment Info | Developer | Add New Field | 29.25 | 2024-04-01 | 2024-09-01 | 37 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-48 | Sprint-48 | Segment Info | Developer | Add Validation | 30.25 | 2024-04-01 | 2024-09-01 | 38 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-48 | Sprint-48 | Segment Info | Developer | Change Validation | 31.25 | 2024-04-01 | 2024-09-01 | 39 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-48 | Sprint-48 | Segment Info | Developer | Create CRUD | 32.25 | 2024-04-01 | 2024-09-01 | 40 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-48 | Sprint-48 | Segment Info | Developer | Modify CRUD | 33.25 | 2024-04-01 | 2024-09-01 | 41 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-48 | Sprint-48 | Segment Info | Developer | Remove Constraint | 34.25 | 2024-04-01 | 2024-09-01 | 42 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-48 | Sprint-48 | Segment Info | Developer | Remove New Field | 35.25 | 2024-04-01 | 2024-09-01 | 43 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-48 | Sprint-48 | Segment Info | Developer | Update Data strcture sheet | 36.25 | 2024-04-01 | 2024-09-01 | 44 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Add Constraint | 37.25 | 2024-04-01 | 2024-09-01 | 45 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Add New Field | 38.25 | 2024-04-01 | 2024-09-01 | 46 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 3 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Add Validation | 39.25 | 2024-04-01 | 2024-09-01 | 47 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 4 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Change Validation | 40.25 | 2024-04-01 | 2024-09-01 | 48 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 5 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Create CRUD | 41.25 | 2024-04-01 | 2024-09-01 | 49 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 6 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Modify CRUD | 42.25 | 2024-04-01 | 2024-09-01 | 50 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 7 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Remove Constraint | 43.25 | 2024-04-01 | 2024-09-01 | 51 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 8 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Remove New Field | 44.25 | 2024-04-01 | 2024-09-01 | 52 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 9 | Sprint-48 | Sprint-48 | Stock And Commodity Info | Developer | Update Data strcture sheet | 45.25 | 2024-04-01 | 2024-09-01 | 53 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 10 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Add Constraint | 46.25 | 2024-04-01 | 2024-09-01 | 54 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 11 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Add New Field | 47.25 | 2024-04-01 | 2024-09-01 | 55 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 12 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Add Validation | 48.25 | 2024-04-01 | 2024-09-01 | 56 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 13 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Change Validation | 49.25 | 2024-04-01 | 2024-09-01 | 57 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 14 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Create CRUD | 50.25 | 2024-04-01 | 2024-09-01 | 58 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 15 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Modify CRUD | 51.25 | 2024-04-01 | 2024-09-01 | 59 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 16 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Remove Constraint | 52.25 | 2024-04-01 | 2024-09-01 | 60 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 17 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Remove New Field | 53.25 | 2024-04-01 | 2024-09-01 | 61 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 18 | Sprint-48 | Sprint-48 | Stock Cap Classification | Developer | Update Data strcture sheet | 54.25 | 2024-04-01 | 2024-09-01 | 62 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 19 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Add Constraint | 55.25 | 2024-04-01 | 2024-09-01 | 63 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 20 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Add New Field | 56.25 | 2024-04-01 | 2024-09-01 | 64 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 21 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Add Validation | 57.25 | 2024-04-01 | 2024-09-01 | 65 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 22 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Change Validation | 58.25 | 2024-04-01 | 2024-09-01 | 66 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 23 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Create CRUD | 59.25 | 2024-04-01 | 2024-09-01 | 67 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 24 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Modify CRUD | 60.25 | 2024-04-01 | 2024-09-01 | 68 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 25 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Remove Constraint | 61.25 | 2024-04-01 | 2024-09-01 | 69 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 26 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Remove New Field | 62.25 | 2024-04-01 | 2024-09-01 | 70 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 27 | Sprint-48 | Sprint-48 | Stock Segment | Developer | Update Data strcture sheet | 63.25 | 2024-04-01 | 2024-09-01 | 71 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 28 | Sprint-48 | Sprint-48 | Charges Info | Developer | Add Constraint | 64.25 | 2024-04-01 | 2024-09-01 | 72 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 29 | Sprint-48 | Sprint-48 | Charges Info | Developer | Add New Field | 65.25 | 2024-04-01 | 2024-09-01 | 73 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 30 | Sprint-48 | Sprint-48 | Charges Info | Developer | Add Validation | 66.25 | 2024-04-01 | 2024-09-01 | 74 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 31 | Sprint-48 | Sprint-48 | Charges Info | Developer | Change Validation | 67.25 | 2024-04-01 | 2024-09-01 | 75 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 32 | Sprint-48 | Sprint-48 | Charges Info | Developer | Create CRUD | 68.25 | 2024-04-01 | 2024-09-01 | 76 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 33 | Sprint-48 | Sprint-48 | Charges Info | Developer | Modify CRUD | 69.25 | 2024-04-01 | 2024-09-01 | 77 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 34 | Sprint-48 | Sprint-48 | Charges Info | Developer | Remove Constraint | 70.25 | 2024-04-01 | 2024-09-01 | 78 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 35 | Sprint-48 | Sprint-48 | Charges Info | Developer | Remove New Field | 71.25 | 2024-04-01 | 2024-09-01 | 79 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 36 | Sprint-48 | Sprint-48 | Charges Info | Developer | Update Data strcture sheet | 72.25 | 2024-04-01 | 2024-09-01 | 80 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 37 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Add Constraint | 73.25 | 2024-04-01 | 2024-09-01 | 81 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 38 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Add New Field | 74.25 | 2024-04-01 | 2024-09-01 | 82 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 39 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Add Validation | 75.25 | 2024-04-01 | 2024-09-01 | 83 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 40 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Change Validation | 76.25 | 2024-04-01 | 2024-09-01 | 84 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 41 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Create CRUD | 77.25 | 2024-04-01 | 2024-09-01 | 85 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 42 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Modify CRUD | 78.25 | 2024-04-01 | 2024-09-01 | 86 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 43 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Remove Constraint | 79.25 | 2024-04-01 | 2024-09-01 | 87 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 44 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Remove New Field | 80.25 | 2024-04-01 | 2024-09-01 | 88 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 45 | Sprint-48 | Sprint-48 | Exposure Info | Developer | Update Data strcture sheet | 81.25 | 2024-04-01 | 2024-09-01 | 89 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 46 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Add Constraint | 82.25 | 2024-04-01 | 2024-09-01 | 90 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 47 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Add New Field | 83.25 | 2024-04-01 | 2024-09-01 | 91 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 48 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Add Validation | 84.25 | 2024-04-01 | 2024-09-01 | 92 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 49 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Change Validation | 85.25 | 2024-04-01 | 2024-09-01 | 93 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 50 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Create CRUD | 86.25 | 2024-04-01 | 2024-09-01 | 94 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 51 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Modify CRUD | 87.25 | 2024-04-01 | 2024-09-01 | 95 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 52 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Remove Constraint | 88.25 | 2024-04-01 | 2024-09-01 | 96 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 53 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Remove New Field | 89.25 | 2024-04-01 | 2024-09-01 | 97 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 54 | Sprint-48 | Sprint-48 | Stock Performance | Developer | Update Data strcture sheet | 90.25 | 2024-04-01 | 2024-09-01 | 98 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 55 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Add Constraint | 91.25 | 2024-04-01 | 2024-09-01 | 99 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 56 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Add New Field | 92.25 | 2024-04-01 | 2024-09-01 | 100 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 57 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Add Validation | 93.25 | 2024-04-01 | 2024-09-01 | 101 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 58 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Change Validation | 94.25 | 2024-04-01 | 2024-09-01 | 102 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 59 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Create CRUD | 95.25 | 2024-04-01 | 2024-09-01 | 103 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 60 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Modify CRUD | 96.25 | 2024-04-01 | 2024-09-01 | 104 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 61 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Remove Constraint | 97.25 | 2024-04-01 | 2024-09-01 | 105 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 62 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Remove New Field | 98.25 | 2024-04-01 | 2024-09-01 | 106 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 63 | Sprint-48 | Sprint-48 | Stock TechnicalInfo | Developer | Update Data strcture sheet | 99.25 | 2024-04-01 | 2024-09-01 | 107 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 64 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Add Constraint | 100.25 | 2024-04-01 | 2024-09-01 | 108 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 65 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Add New Field | 101.25 | 2024-04-01 | 2024-09-01 | 109 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 66 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Add Validation | 102.25 | 2024-04-01 | 2024-09-01 | 110 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 67 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Change Validation | 103.25 | 2024-04-01 | 2024-09-01 | 111 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 68 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Create CRUD | 104.25 | 2024-04-01 | 2024-09-01 | 112 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 69 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Modify CRUD | 105.25 | 2024-04-01 | 2024-09-01 | 113 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 70 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Remove Constraint | 106.25 | 2024-04-01 | 2024-09-01 | 114 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 71 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Remove New Field | 107.25 | 2024-04-01 | 2024-09-01 | 115 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 72 | Sprint-48 | Sprint-48 | Stock Transaction | Developer | Update Data strcture sheet | 108.25 | 2024-04-01 | 2024-09-01 | 116 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 73 | Sprint-48 | Sprint-48 | User Broker | Developer | Add Constraint | 109.25 | 2024-04-01 | 2024-09-01 | 117 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 74 | Sprint-48 | Sprint-48 | User Broker | Developer | Add New Field | 110.25 | 2024-04-01 | 2024-09-01 | 118 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 75 | Sprint-48 | Sprint-48 | User Broker | Developer | Add Validation | 111.25 | 2024-04-01 | 2024-09-01 | 119 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 76 | Sprint-48 | Sprint-48 | User Broker | Developer | Change Validation | 112.25 | 2024-04-01 | 2024-09-01 | 120 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 77 | Sprint-48 | Sprint-48 | User Broker | Developer | Create CRUD | 113.25 | 2024-04-01 | 2024-09-01 | 121 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 78 | Sprint-48 | Sprint-48 | User Broker | Developer | Modify CRUD | 114.25 | 2024-04-01 | 2024-09-01 | 122 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 79 | Sprint-48 | Sprint-48 | User Broker | Developer | Remove Constraint | 115.25 | 2024-04-01 | 2024-09-01 | 123 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 80 | Sprint-48 | Sprint-48 | User Broker | Developer | Remove New Field | 116.25 | 2024-04-01 | 2024-09-01 | 124 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 81 | Sprint-48 | Sprint-48 | User Broker | Developer | Update Data strcture sheet | 117.25 | 2024-04-01 | 2024-09-01 | 125 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 82 | Sprint-48 | Sprint-48 | User Segment | Developer | Add Constraint | 118.25 | 2024-04-01 | 2024-09-01 | 126 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 83 | Sprint-48 | Sprint-48 | User Segment | Developer | Add New Field | 119.25 | 2024-04-01 | 2024-09-01 | 127 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 84 | Sprint-48 | Sprint-48 | User Segment | Developer | Add Validation | 120.25 | 2024-04-01 | 2024-09-01 | 128 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 85 | Sprint-48 | Sprint-48 | User Segment | Developer | Change Validation | 121.25 | 2024-04-01 | 2024-09-01 | 129 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 86 | Sprint-48 | Sprint-48 | User Segment | Developer | Create CRUD | 122.25 | 2024-04-01 | 2024-09-01 | 130 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 87 | Sprint-48 | Sprint-48 | User Segment | Developer | Modify CRUD | 123.25 | 2024-04-01 | 2024-09-01 | 131 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 88 | Sprint-48 | Sprint-48 | User Segment | Developer | Remove Constraint | 124.25 | 2024-04-01 | 2024-09-01 | 132 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 89 | Sprint-48 | Sprint-48 | User Segment | Developer | Remove New Field | 125.25 | 2024-04-01 | 2024-09-01 | 133 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 90 | Sprint-48 | Sprint-48 | User Segment | Developer | Update Data strcture sheet | 126.25 | 2024-04-01 | 2024-09-01 | 134 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 91 | Sprint-48 | Sprint-48 | User Stock | Developer | Add Constraint | 127.25 | 2024-04-01 | 2024-09-01 | 135 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 92 | Sprint-48 | Sprint-48 | User Stock | Developer | Add New Field | 128.25 | 2024-04-01 | 2024-09-01 | 136 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 93 | Sprint-48 | Sprint-48 | User Stock | Developer | Add Validation | 129.25 | 2024-04-01 | 2024-09-01 | 137 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 94 | Sprint-48 | Sprint-48 | User Stock | Developer | Change Validation | 130.25 | 2024-04-01 | 2024-09-01 | 138 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 95 | Sprint-48 | Sprint-48 | User Stock | Developer | Create CRUD | 131.25 | 2024-04-01 | 2024-09-01 | 139 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 96 | Sprint-48 | Sprint-48 | User Stock | Developer | Modify CRUD | 132.25 | 2024-04-01 | 2024-09-01 | 140 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 97 | Sprint-48 | Sprint-48 | User Stock | Developer | Remove Constraint | 133.25 | 2024-04-01 | 2024-09-01 | 141 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 98 | Sprint-48 | Sprint-48 | User Stock | Developer | Remove New Field | 134.25 | 2024-04-01 | 2024-09-01 | 142 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 99 | Sprint-48 | Sprint-48 | User Stock | Developer | Update Data strcture sheet | 135.25 | 2024-04-01 | 2024-09-01 | 143 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 100 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Add Constraint | 136.25 | 2024-04-01 | 2024-09-01 | 144 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 101 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Add New Field | 137.25 | 2024-04-01 | 2024-09-01 | 145 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 102 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Add Validation | 138.25 | 2024-04-01 | 2024-09-01 | 146 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 103 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Change Validation | 139.25 | 2024-04-01 | 2024-09-01 | 147 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 104 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Create CRUD | 140.25 | 2024-04-01 | 2024-09-01 | 148 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 105 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Modify CRUD | 141.25 | 2024-04-01 | 2024-09-01 | 149 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 106 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Remove Constraint | 142.25 | 2024-04-01 | 2024-09-01 | 150 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 107 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Remove New Field | 143.25 | 2024-04-01 | 2024-09-01 | 151 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 108 | Sprint-48 | Sprint-48 | Income Hair Cut | Developer | Update Data strcture sheet | 144.25 | 2024-04-01 | 2024-09-01 | 152 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 109 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Add Constraint | 145.25 | 2024-04-01 | 2024-09-01 | 153 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 110 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Add New Field | 146.25 | 2024-04-01 | 2024-09-01 | 154 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 111 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Add Validation | 147.25 | 2024-04-01 | 2024-09-01 | 155 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 112 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Change Validation | 148.25 | 2024-04-01 | 2024-09-01 | 156 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 113 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Create CRUD | 149.25 | 2024-04-01 | 2024-09-01 | 157 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 114 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Modify CRUD | 150.25 | 2024-04-01 | 2024-09-01 | 158 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 115 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Remove Constraint | 151.25 | 2024-04-01 | 2024-09-01 | 159 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 116 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Remove New Field | 152.25 | 2024-04-01 | 2024-09-01 | 160 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 117 | Sprint-48 | Sprint-48 | Loan Cheque Mortgage | Developer | Update Data strcture sheet | 153.25 | 2024-04-01 | 2024-09-01 | 161 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 118 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Add Constraint | 154.25 | 2024-04-01 | 2024-09-01 | 162 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 119 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Add New Field | 155.25 | 2024-04-01 | 2024-09-01 | 163 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 120 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Add Validation | 156.25 | 2024-04-01 | 2024-09-01 | 164 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 121 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Change Validation | 157.25 | 2024-04-01 | 2024-09-01 | 165 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 122 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Create CRUD | 158.25 | 2024-04-01 | 2024-09-01 | 166 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 123 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Modify CRUD | 159.25 | 2024-04-01 | 2024-09-01 | 167 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 124 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Remove Constraint | 160.25 | 2024-04-01 | 2024-09-01 | 168 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 125 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Remove New Field | 161.25 | 2024-04-01 | 2024-09-01 | 169 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 126 | Sprint-48 | Sprint-48 | Loan Cheque Transaction | Developer | Update Data strcture sheet | 162.25 | 2024-04-01 | 2024-09-01 | 170 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 127 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Add Constraint | 163.25 | 2024-04-01 | 2024-09-01 | 171 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 128 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Add New Field | 164.25 | 2024-04-01 | 2024-09-01 | 172 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 129 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Add Validation | 165.25 | 2024-04-01 | 2024-09-01 | 173 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 130 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Change Validation | 166.25 | 2024-04-01 | 2024-09-01 | 174 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 131 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Create CRUD | 167.25 | 2024-04-01 | 2024-09-01 | 175 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 132 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Modify CRUD | 168.25 | 2024-04-01 | 2024-09-01 | 176 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 133 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Remove Constraint | 169.25 | 2024-04-01 | 2024-09-01 | 177 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 134 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Remove New Field | 170.25 | 2024-04-01 | 2024-09-01 | 178 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 135 | Sprint-48 | Sprint-48 | Loan Closure | Developer | Update Data strcture sheet | 171.25 | 2024-04-01 | 2024-09-01 | 179 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 136 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Add Constraint | 172.25 | 2024-04-01 | 2024-09-01 | 180 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 137 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Add New Field | 173.25 | 2024-04-01 | 2024-09-01 | 181 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 138 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Add Validation | 174.25 | 2024-04-01 | 2024-09-01 | 182 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 139 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Change Validation | 175.25 | 2024-04-01 | 2024-09-01 | 183 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 140 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Create CRUD | 176.25 | 2024-04-01 | 2024-09-01 | 184 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 141 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Modify CRUD | 177.25 | 2024-04-01 | 2024-09-01 | 185 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 142 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Remove Constraint | 178.25 | 2024-04-01 | 2024-09-01 | 186 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 143 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Remove New Field | 179.25 | 2024-04-01 | 2024-09-01 | 187 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 144 | Sprint-48 | Sprint-48 | Loan Disburshment | Developer | Update Data strcture sheet | 180.25 | 2024-04-01 | 2024-09-01 | 188 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 145 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Add Constraint | 181.25 | 2024-04-01 | 2024-09-01 | 189 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 146 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Add New Field | 182.25 | 2024-04-01 | 2024-09-01 | 190 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 147 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Add Validation | 183.25 | 2024-04-01 | 2024-09-01 | 191 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 148 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Change Validation | 184.25 | 2024-04-01 | 2024-09-01 | 192 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 149 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Create CRUD | 185.25 | 2024-04-01 | 2024-09-01 | 193 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 150 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Modify CRUD | 186.25 | 2024-04-01 | 2024-09-01 | 194 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 151 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Remove Constraint | 187.25 | 2024-04-01 | 2024-09-01 | 195 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 152 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Remove New Field | 188.25 | 2024-04-01 | 2024-09-01 | 196 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 153 | Sprint-48 | Sprint-48 | Loan Proposal | Developer | Update Data strcture sheet | 189.25 | 2024-04-01 | 2024-09-01 | 197 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 154 | Sprint-48 | Sprint-48 | Loan Request | Developer | Add Constraint | 190.25 | 2024-04-01 | 2024-09-01 | 198 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 155 | Sprint-48 | Sprint-48 | Loan Request | Developer | Add New Field | 191.25 | 2024-04-01 | 2024-09-01 | 199 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 156 | Sprint-48 | Sprint-48 | Loan Request | Developer | Add Validation | 192.25 | 2024-04-01 | 2024-09-01 | 200 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 157 | Sprint-48 | Sprint-48 | Loan Request | Developer | Change Validation | 193.25 | 2024-04-01 | 2024-09-01 | 201 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 158 | Sprint-48 | Sprint-48 | Loan Request | Developer | Create CRUD | 194.25 | 2024-04-01 | 2024-09-01 | 202 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 159 | Sprint-48 | Sprint-48 | Loan Request | Developer | Modify CRUD | 195.25 | 2024-04-01 | 2024-09-01 | 203 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 160 | Sprint-48 | Sprint-48 | Loan Request | Developer | Remove Constraint | 196.25 | 2024-04-01 | 2024-09-01 | 204 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 161 | Sprint-48 | Sprint-48 | Loan Request | Developer | Remove New Field | 197.25 | 2024-04-01 | 2024-09-01 | 205 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 162 | Sprint-48 | Sprint-48 | Loan Request | Developer | Update Data strcture sheet | 198.25 | 2024-04-01 | 2024-09-01 | 206 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 163 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Add Constraint | 199.25 | 2024-04-01 | 2024-09-01 | 207 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 164 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Add New Field | 200.25 | 2024-04-01 | 2024-09-01 | 208 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 165 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Add Validation | 201.25 | 2024-04-01 | 2024-09-01 | 209 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 166 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Change Validation | 202.25 | 2024-04-01 | 2024-09-01 | 210 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 167 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Create CRUD | 203.25 | 2024-04-01 | 2024-09-01 | 211 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 168 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Modify CRUD | 204.25 | 2024-04-01 | 2024-09-01 | 212 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 169 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Remove Constraint | 205.25 | 2024-04-01 | 2024-09-01 | 213 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 170 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Remove New Field | 206.25 | 2024-04-01 | 2024-09-01 | 214 | 2024-04-01 | 2024-09-01
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 171 | Sprint-48 | Sprint-48 | Loan To NPA | Developer | Update Data strcture sheet | 207.25 | 2024-04-01 | 2024-09-01 | 215 | 2024-04-01 | 2024-09-01

## 17_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-47 | Add Constraint
Sprint-47 | Add New Field
Sprint-47 | Add Validation
Sprint-47 | Change Validation
Sprint-47 | Create CRUD
Sprint-47 | Modify CRUD
Sprint-47 | Remove Constraint
Sprint-47 | Remove New Field
Sprint-47 | Update Data strcture sheet
Sprint-48 | Add Constraint
Sprint-48 | Add New Field
Sprint-48 | Add Validation
Sprint-48 | Change Validation
Sprint-48 | Create CRUD
Sprint-48 | Modify CRUD
Sprint-48 | Remove Constraint
Sprint-48 | Remove New Field
Sprint-48 | Update Data strcture sheet

## 18_TaskAssignment
UniqueUserId | FeatureTaskName | TaskHurdleName | StoryPoint | StartDate | EndDate | IsCompleted | IsOnHold
FFM000001 | Create CRUD | Unfamilar with subject | 2 | 2024-04-01 | 2024-09-01 | FALSE | TRUE

## 19_WorkmanTimesheet
FillUpOn | UniqueUserId | StepInAt | StepOutAt | TotalInTime | TimesheetTime | BillableTime | OfficeAcitivityTime | IdleTime | TaskName | StatusName | IsWorkDone | AttachInAppriasal | ValuableContribution | UserPreferredName
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Create CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi