## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-53 | 2025-02-01 | 2025-02-15
Sprint-54 | 2025-02-16 | 2020-03-28

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject | AllocationFrequencyName | ProjectRoleName
Estimate Cost Guidance | Estimate Cost Guidance | TRUE | Product | Full Stack Development | Estimate Cost Guidance | ritesh.mangi@soartechnologies.net | FALSE | FALSE | Allocated-Hour | Project Management

## 12_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Estimate Cost Guidance | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 13_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Estimate Cost Guidance | Estimate Cost Guidance | ECG | Development Started

## 14_ModuleFeatures
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Estimate Cost Guidance | Component Wise Resourse | DEF | 788 | Web
Estimate Cost Guidance | Drawing Wise Component | CNT | 789 | Web
Estimate Cost Guidance | Lead Wise Drawing | DEF | 790 | Web
Estimate Cost Guidance | Material | CNT | 791 | Web
Estimate Cost Guidance | MOC | DEF | 792 | Web
Estimate Cost Guidance | MOC Pricing | CNT | 793 | Web
Estimate Cost Guidance | Parameter Info | DEF | 794 | Web
Estimate Cost Guidance | Shape MOC | CNT | 795 | Web
Estimate Cost Guidance | Shape Parameter | DEF | 796 | Web
Estimate Cost Guidance | Shapes | CNT | 797 | Web

## 15_ProjectTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Add Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Add New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Add Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Change Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Create CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Modify CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Remove Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Remove New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-53 | Sprint-53 | Component Wise Resourse | Developer | Update Data strcture sheet | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Add Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Add New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Add Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Change Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Create CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Modify CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Remove Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Remove New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-53 | Sprint-53 | Drawing Wise Component |  | Update Data strcture sheet | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Lead Wise Drawing |  | Add Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Lead Wise Drawing |  | Add New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Lead Wise Drawing |  | Add Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-53 | Sprint-53 | Lead Wise Drawing |  | Change Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-53 | Sprint-53 | Lead Wise Drawing |  | Create CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-54 | Sprint-54 | Lead Wise Drawing |  | Modify CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-54 | Sprint-54 | Lead Wise Drawing |  | Remove Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-54 | Sprint-54 | Lead Wise Drawing |  | Remove New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-54 | Sprint-54 | Lead Wise Drawing |  | Update Data strcture sheet | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-54 | Sprint-54 | Material |  | Add Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-54 | Sprint-54 | Material |  | Add New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-54 | Sprint-54 | Material |  | Add Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-54 | Sprint-54 | Material |  | Change Validation | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-54 | Sprint-54 | Material |  | Create CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-54 | Sprint-54 | Material |  | Modify CRUD | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-54 | Sprint-54 | Material |  | Remove Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-54 | Sprint-54 | Material |  | Remove New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-54 | Sprint-54 | Material |  | Update Data strcture sheet | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-54 | Sprint-54 | MOC |  | Add Constraint | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-54 | Sprint-54 | MOC |  | Add New Field | 0.25 | 2025-02-01 | 2025-02-25 | 8 | 2025-02-01 | 2025-02-25

## 17_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-53 | Add Constraint
Sprint-53 | Add New Field
Sprint-53 | Add Validation
Sprint-53 | Change Validation
Sprint-53 | Create CRUD
Sprint-53 | Modify CRUD
Sprint-53 | Remove Constraint
Sprint-53 | Remove New Field
Sprint-53 | Update Data strcture sheet

## 18_TaskAssignment
UniqueUserId | FeatureTaskName | TaskHurdleName | StoryPoint | StartDate | EndDate | IsCompleted | IsOnHold
FFM000001 | Remove Constraint | Hardware and Software Issue | 4 | 2025-02-01 | 2025-02-25 | TRUE | FALSE

## 19_WorkmanTimesheet
FillUpOn | UniqueUserId | StepInAt | StepOutAt | TotalInTime | TimesheetTime | BillableTime | OfficeAcitivityTime | IdleTime | TaskName | StatusName | IsWorkDone | AttachInAppriasal | ValuableContribution | UserPreferredName
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi