## 01_Sprint
SprintName | SprintStartDate | SprintEndDate
Sprint-55 | 2025-04-01 | 2025-04-15
Sprint-56 | 2025-04-16 | 2025-04-30

## 11_ClientProjectInfo
ProgramName | ProjectName | HasWBS | ProjectType | DepartmentName | ProjectDescription | ProjectOwnerEmail | IsInternalProject | IsDefaultProject | AllocationFrequencyName | ProjectRoleName
Satsang | Satsang | TRUE | Product | Full Stack Development | Satsang | ritesh.mangi@soartechnologies.net | FALSE | FALSE | Allocated-Hour | Project Management

## 12_ProjectMilestone
MilestoneName | MilestoneDescription | DueDate | ProjectName | CompletedOn | ClosedOn | CancelledOn | IsClosed | IsCompleted | IsCancelled
Development Started | Fist leve Done | 2025-08-19 | Satsang | 2025-08-19 | 2025-08-19 |  | TRUE | TRUE | FALSE

## 13_ProjectModule
ProjectName | ModuleName | ModuleCode | ProjectMilestoneName
Satsang | Internal Comunication Tool | ICT | Development Started

## 14_ModuleFeatures
ModuleName | FeatureName | FeaturePrefix | FeaturePriority | PlatformTypeName
Internal Comunication Tool | Chat Group | DEF | 494 | Web
Internal Comunication Tool | Chat Group Type | CNT | 495 | Web
Internal Comunication Tool | Chat Message Type | DEF | 496 | Web
Internal Comunication Tool | Chat Group User | CNT | 497 | Web
Internal Comunication Tool | Chat Message Tagged User | DEF | 498 | Web
Internal Comunication Tool | Chat Messenger | CNT | 499 | Web
Internal Comunication Tool | DND Groups | DEF | 500 | Web
Internal Comunication Tool | DND Users | CNT | 501 | Web
Internal Comunication Tool | Message Broadcast | DEF | 502 | Web
Internal Comunication Tool | Pinned To Top Groups | CNT | 503 | Web
Internal Comunication Tool | Pinned To Top Message | DEF | 504 | Web
Internal Comunication Tool | Pinned To Top User | CNT | 505 | Web

## 15_ProjectTask
TaskDelayReasonName | TaskFrequencyName | StatusName | TaskLifeCycleName | TaskTypeName | StoryPoint | StartingSprintName | EndingSprintName | FeatureName | TaskRoleName | TaskName | EstimatedHours | EstimatedStartDate | EstimatedEndDate | ActualHours | ActualStartDate | ActualEndDate
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 2 | Sprint-55 | Sprint-55 | Chat Group | Developer | Add Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group | Developer | Add New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group | Developer | Add Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group | Developer | Change Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group | Developer | Create CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 2 | Sprint-55 | Sprint-55 | Chat Group | Developer | Modify CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group | Developer | Remove Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group | Developer | Remove New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 2 | Sprint-55 | Sprint-55 | Chat Group | Developer | Update Data strcture sheet | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Add Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Add New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Add Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Change Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Create CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Modify CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Remove Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Remove New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 2 | Sprint-55 | Sprint-55 | Chat Group Type | Developer | Update Data strcture sheet | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group User | Developer | Add Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group User | Developer | Add New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Ready for Development | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group User | Developer | Add Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Initiated | Completed | Quick and Easy | 1 | Sprint-55 | Sprint-55 | Chat Group User | Developer | Change Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-55 | Sprint-55 | Chat Group User | Developer | Create CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-55 | Sprint-55 | Chat Group User | Developer | Modify CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-56 | Sprint-56 | Chat Group User | Developer | Remove Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 1 | Sprint-56 | Sprint-56 | Chat Group User | Developer | Remove New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 1 | Sprint-56 | Sprint-56 | Chat Group User | Developer | Update Data strcture sheet | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Add Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Add New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Quick and Easy | 2 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Add Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Quick and Easy | 2 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Change Validation | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Create CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 2 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Modify CRUD | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Remove Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Remove New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 1 | Sprint-56 | Sprint-56 | Chat Message Tagged User | Developer | Update Data strcture sheet | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Ready for Development | Medium | 1 | Sprint-56 | Sprint-56 | Chat Message TaggedUser | Developer | Add Constraint | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29
Not Delayed | TaskRecurring-Hourly | Completed | Completed | Medium | 2 | Sprint-56 | Sprint-56 | Chat Message TaggedUser | Developer | Add New Field | 0.25 | 2025-04-01 | 2025-04-29 | 8 | 2025-04-01 | 2025-04-29

## 17_TaskSprintHistory
SprintName | FeatureTaskName
Sprint-56 | Add Constraint
Sprint-56 | Add New Field
Sprint-56 | Add Validation
Sprint-56 | Change Validation
Sprint-56 | Create CRUD
Sprint-56 | Modify CRUD
Sprint-56 | Remove Constraint
Sprint-56 | Remove New Field
Sprint-56 | Update Data strcture sheet

## 18_TaskAssignment
UniqueUserId | FeatureTaskName | TaskHurdleName | StoryPoint | StartDate | EndDate | IsCompleted | IsOnHold
FFM000001 | Modify CRUD | Hardware and Software Issue | 9 | 2025-04-01 | 2025-04-29 | TRUE | FALSE

## 19_WorkmanTimesheet
FillUpOn | UniqueUserId | StepInAt | StepOutAt | TotalInTime | TimesheetTime | BillableTime | OfficeAcitivityTime | IdleTime | TaskName | StatusName | IsWorkDone | AttachInAppriasal | ValuableContribution | UserPreferredName
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Modify CRUD | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi
2025-Sep-26 19:25:00 | FFM000001 | 2025-Sep-26 10:00:00 | 2025-Sep-26 19:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | 2025-Sep-26 09:30:00 | Add Constraint | Completed | TRUE | TRUE | TRUE | [FFM000002] - Neha Riteshkumar Mangi